## Grantt Chart
Task Name | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
Phase 1: Design | bar: Week 1 to Week 2
Requirement Analysis | bar: Week 1
Data Source Selection | bar: Week 2
Phase 2: Development | bar: Week 3 to Week 6
API & Logic Coding | bar: Week 3 to Week 4
UI & Map Integration | bar: Week 5 to Week 6
Phase 3: Finalize | bar: Week 7 to Week 8
Testing & Bug Fixes | bar: Week 7
Report Writing | bar: Week 7 to Week 8
Submission | bar: Week 8